【内部填写说明，发送前整段删除】

本稿只回答 Iara 9 月 13 日 WhatsApp 的两问：RNP 侧需要什么技能的人、需要多少人。内容先按 9 月 9 日英文 PPT 填充（第 3、12、13 页与附录 A3、A6、A7、A10）。PPT 没有的地方用黄底 [TBC: …] 标出，需要你手工填。

1. 人数口径要二选一：PPT 第 13 页写三批约 30 / 20 / 30 人，附录 A7 按岗位合计为 53 / 25 / 33 人。本稿正文按 A7 的岗位明细填，总览表下有一条黄底提示，定稿前统一成一套。

2. 各岗位的背景要求：PPT 只写了各角色参与什么工作，没有写学历、经验年限等要求，全部标 TBC。

3. 移交后常设人数：PPT 没有数字，会上口头说过 15 到 20 人，是否写入由你定。

4. 到位提前量与 T0 日期：PPT 只说 T0 为首批算力就绪、逐月日期实施前商定。

5. 讯飞对口团队：PPT 没有列，第 4 节留空待填。

6. 可短期外借的岗位：会上口头说过语言专家和领域专家只需半年到九个月，可请高校人员短期参与，是否写入由你定。

RNP Team for the Technology Transfer

Skills and headcount RNP needs on its side, by team and by project step

iFLYTEK input to RNP's team planning  ·  Draft v0.1  ·  14 September 2026  ·  Follows the presentation of 9 September 2026

Further to your message of 13 September, this note sets out what RNP needs on its side to receive the technology transfer and to work with iFLYTEK during the project: which teams, what skills, how many people, and from when. It is drawn from the presentation of 9 September and its appendices, so RNP can plan from one consistent picture.

All headcounts are indicative. They are iFLYTEK's early estimate of the peak per function; a person can cover more than one activity, so they are not people on site at the same time. Final numbers follow the SOW split of work and the month-by-month schedule agreed before implementation.

# 1.  The RNP team at a glance

Eight teams. The first four start with Step 1 (platform and corpus), the next two with Step 2 (model training and evaluation), the last two with Step 3 (application and DLM). Source: deck p.13 and Appendix A7.

| Team | What the team does with iFLYTEK | Core skills | People | Needed from |
| --- | --- | --- | --- | --- |
| 1 Project and product | Requirements, schedule, resources and delivery; coordinates Huawei compute and environment; organises acceptance; defines the National AI Application with iFLYTEK (functions, user scope, content rules) | Project management; product definition; data-centre coordination | 9 | Step 1 |
| 2 Corpus and data | Organises data acquisition, licensing and full-volume production of the Portuguese corpus; runs the corpus pilot batch with iFLYTEK's specifications and sampling checks | Data sourcing and licensing; data processing on the platform; annotation and quality control | 32 | Step 1 |
| 3 Portuguese language experts | Sets Portuguese quality, annotation rules, safety labels and speech standards; checks samples | Brazilian Portuguese linguistics; annotation standards; speech data | 6 | Step 1 |
| 4 Compliance and review | Content, safety and legal review; secures corpus licences; runs the Content Safety Review Platform after acceptance | Content safety policy; data and IP law; review operations | 6 | Step 1 |
| 5 Business and domain experts | Confirms the business scenarios for the three Domain Large Models; assesses domain results | Domain knowledge for the chosen scenarios; requirements; evaluation of model output | 7 | Step 2 |
| 6 Model and test engineering | Joins national model training and evaluation in the Model Training Center; then trains the DLMs with iFLYTEK advising | LLM training and evaluation on the platform; test and validation | 18 | Step 2 |
| 7 Application and operations | Takes over the National AI Application: architecture, integration, user approval, content and daily operations | Software development; application operations; architecture | 27 | Step 3 |
| 8 Platform O&M | Runs the platform after acceptance: monitoring, deployment, incidents, escalation; assisted O&M with iFLYTEK for 12 months | Cluster and platform operations; incident and change management | 6 | Step 3 |
| Total (peak per function) |  |  | 111 |  |

[TBC: The deck headline (p.13) gives about 30 / 20 / 30 people per intake; the A7 detail above sums to 53 / 25 / 33. Confirm one set of figures before sending.]

[TBC: Permanent team RNP keeps after handover (development vs operations): not stated in the deck.]

# 2.  Skills by role

Each team broken down by role, with what each role must be able to do. Role composition from Appendix A7; activities from Appendix A10 and A3. Background requirements are open for RNP's HR to align with its own job profiles.

## Team 1  Project and product  (9)

| Role | People | Must be able to | Background |
| --- | --- | --- | --- |
| Project manager | 2 | Run the five-step schedule with iFLYTEK and Huawei; manage resources, risks and delivery; organise component and final acceptance | [TBC: e.g. large IT/infrastructure programme delivery] |
| Product manager | 4 | Define the National AI Application with iFLYTEK: functions, user scope, content rules, Brazilian content and roadmap | [TBC] |
| PMO / data-centre expert | 3 | Coordinate Huawei compute, facilities, network and base environment; track T0 and compute batches | [TBC] |

## Team 2  Corpus and data  (32)

| Role | People | Must be able to | Background |
| --- | --- | --- | --- |
| Data resource engineer | 6 | Identify data sources, secure licences and permitted use, organise acquisition; store project data in the RNP-designated Brazilian environment | [TBC] |
| Data quality engineer | 6 | Apply the agreed counting, sampling, quality-threshold, batching and re-check rules; run the corpus pilot batch; operate the Corpus Construction Center (ingest, clean, de-duplicate, quality metrics) | [TBC] |
| Annotator | 20 | Annotate to the agreed standards: 200,000 supervised samples, 20,000 safety and values samples, transcription of 10,000 hours of speech | [TBC] |

## Team 3  Portuguese language experts  (6)

| Role | People | Must be able to | Background |
| --- | --- | --- | --- |
| Language expert | 6 | Set Brazilian Portuguese quality standards, annotation rules, safety labels and speech (ASR/TTS) standards; analyse samples and confirm rules with iFLYTEK | [TBC: e.g. linguistics, corpus linguistics, phonetics] |

## Team 4  Compliance and review  (6)

| Role | People | Must be able to | Background |
| --- | --- | --- | --- |
| Review expert | 2 | Define review policies, sensitive lexicons and risk samples on the Content Safety Review Platform; review model and application content | [TBC] |
| Legal expert | 2 | Clear data licences and permitted use; content, safety and legal compliance of corpus, models and application | [TBC] |
| Review lead | 2 | Own the review process and its records; escalate and approve | [TBC] |

## Team 5  Business and domain experts  (7)

| Role | People | Must be able to | Background |
| --- | --- | --- | --- |
| Business requirements | 3 | Define the business scenario for each of the three DLM services; confirm inputs and acceptance of the service | [TBC] |
| Domain requirements | 2 | Specify domain data and expected results; read evaluation reports and set content boundaries | [TBC] |
| Domain expert | 2 | Assess model results in the domain; take part in evaluation exercises with iFLYTEK | [TBC] |

## Team 6  Model and test engineering  (18)

| Role | People | Must be able to | Background |
| --- | --- | --- | --- |
| Algorithm engineer | 12 | Prepare datasets, configure and submit training jobs, read logs and evaluations, release models in the Model Training Center; train the DLMs on the platform with iFLYTEK advising | [TBC: e.g. ML/LLM engineering, Python, distributed training] |
| Test engineer | 6 | Run model evaluation and technical validation against the agreed evaluation rules; document results for acceptance | [TBC] |

## Team 7  Application and operations  (27)

| Role | People | Must be able to | Background |
| --- | --- | --- | --- |
| Software developer | 15 | Integrate the National AI Application (mobile, desktop, web) with RNP systems; develop Brazilian content and features on the delivered baseline; call the platform APIs | [TBC: e.g. mobile/web/back-end development] |
| Operations engineer | 10 | Operate the application: configuration, user approval and permissions, API credentials and rate limits, usage analytics, feedback | [TBC] |
| Architect | 2 | Own application architecture and integration with RNP systems and the platform | [TBC] |

## Team 8  Platform O&M  (6)

| Role | People | Must be able to | Background |
| --- | --- | --- | --- |
| O&M engineer | 6 | Monitor the platform and cluster, handle incidents, changes and common faults, manage deployments and escalation; take over from assisted O&M and run the platform independently | [TBC: e.g. Linux, containers, cluster operations] |

# 3.  When each team is needed

Timing follows the five implementation steps (deck p.12). T0 is the first compute readiness; month-by-month dates are agreed before implementation. Each team should be in place before its step starts.

| Step | Completion markers | Teams that must be in place | People |
| --- | --- | --- | --- |
| 1 Platform and corpus | Platform accepted; corpus pilot batch passes | Project and product; Corpus and data; Portuguese language experts; Compliance and review | 53 |
| 2 Model training and evaluation | Text model passes; speech models pass | Step 1 teams, plus Business and domain experts; Model and test engineering | + 25 |
| 3 Application and DLM | App Stage 1 delivered; DLM forms signed | Steps 1–2 teams, plus Application and operations; Platform O&M | + 33 |
| 4 Acceptance | Component acceptance reports signed | All teams; acceptance organised by Project and product | — |
| 5 Handover and support | Handover signed; assisted O&M begins (12 months on site, then 60 months remote) | Application and operations; Platform O&M; Model engineering for DLMs. [TBC: permanent headcount after handover] | [TBC] |

[TBC: Lead time: how many months before Step 1 the first teams should be recruited and in place; and the planned T0 date.]

# 4.  Working with iFLYTEK

Each RNP team works with one iFLYTEK team throughout its steps, so that the transfer happens on the actual project work rather than in separate sessions.

| RNP team | iFLYTEK counterpart | Where they work together |
| --- | --- | --- |
| Project and product | [TBC: iFLYTEK project management / product team] | Schedule, acceptance, application definition |
| Corpus and data; Portuguese language experts | [TBC: iFLYTEK data / corpus team] | Corpus specifications, pilot batch, sampling checks; Corpus Construction Center |
| Compliance and review | [TBC: iFLYTEK content safety team] | Review policies, lexicons, risk samples |
| Model and test engineering; Business and domain experts | [TBC: iFLYTEK model training / DLM advisory team] | National model training and evaluation; DLM training |
| Application and operations | [TBC: iFLYTEK application team] | Application delivery, integration, operations |
| Platform O&M | [TBC: iFLYTEK O&M / support team] | Assisted O&M, handover, remote support |

# 5.  Notes

- Headcounts are peaks per function and can be reused across activities; they are not people on site at once.

- Under this SOW, RNP takes on data production, DLM training and daily operations, so the figures should be re-checked against the actual split of work once the schedule is fixed.

- [TBC: Which roles can be short-term or drawn from universities and partner institutions, and for how long.]

- iFLYTEK is glad to review RNP's team plan against this note once RNP has a first version.